Meeting Minutes TC 7.6 Research Subcommittee Thursday June. 11, 2020, 1:00 PM–2:00 PM Virtual meeting due to COVID-19 https://zoom.us/j/99592058653?pwd=NzNZcG84dnQ0WGJFeVdqempPKzM2Zz09

- Sign-in / introductions

16 people attended (including two others without sign-in)

| Name | Affiliation | Email Address |
| --- | --- | --- |
| Eric Yang | Energy System Group | ericyangcem@gmail.com |
| Joe Firrantello (JF) | Envinity Inc. | j.firrantello@gmail.com |
| Michael Deru | NREL | Michael.deru@nrel.gov |
| Bruce Hunn | Consultant | hunnbuildingenergy@gmail.com |
| Steven Carlson | XRG |  |
| Nicholas Long | NREL | nicholaslong@nrel.org |
| Curtis Fong | Taylor Engineering | cfong@taylor-engineering.com |
| Jeff Haberl | TAMU |  |
| Hyojin Kim | NJIT | hyojin.kim@njit.edu |
| Ahmed Alla Eldin |  |  |
| Dennis Landsberg | L&S Energy | Dlandsberg@ls-energy.com |
| Michael Bobker | CUNY |  |
| Xiaohui Zhou | Slipstream |  |

- RP-1771 – Modeling of typical commercial buildings in support of the ASHRAE bEQ energy rating program

Principal investigator: Wangda Zuo; one year no cost extension request to March 31, 2021.  18 prototype building types and eight climate zones. Task 5 was completed.  Scheduled to complete by March, 2021.

- RP-1650 –TC 7.3, TC 7.6 co-sponsored – Training requirements for sustainable, high-performance building (HPB) operation

Montana State University is the principal contractor. The draft report is completed and approved by ASHRAE in May 2019.  The final report was approved.

- 1836-RP “Developing a Standardized Categorization System for Energy Efficiency Measures

Amanda provided updates: total three tasks; task 1 (literature review and analysis) was already completed; on time; to be completed by Nov. 2020.

- RP-1814 (co-sponsored with TC 2.8)– Actual Energy Performance of Secondary Schools and Medium Offices Designed to Comply with ASHRAE Standard 90.1-2010

No comments/updates from the meeting.

- Recently completed projects

RP– 1633”Data and Interfaces for Advanced Building Maintenance and Operation” – completed; posted online.

RP–1651“Development of Maximum Technically Achievable Energy Targets for Ultra-Low Energy”– completed one year ago; good feedback from members

RP-1702 – Studies to test the performance measurement protocols (recently completed, goal achieved)

- Topics brought out last conference meeting

- How do the existing buildings (compliant with 90.1) meet the standard requirement of SSPC 100?

Interesting topic to explore further with input from ASHRAE 189 and 90.1

Updates:

- Scott West to obtain the input from ASHRAE 189 (Action)

- Joe F. to obtain the input from ASHRAE 100 (completed); good feedback from ASHRAE 100.

- ASHRAE TC1.4 meeting suggested a research project on the ‘costs and benefits of Cx building controls’, notably including the persistence and longevity impacts. (Scott Hackle)

No updates

- Code compliance secondary research to inform 90.1.  (Scott Hackle)

Action:

- Scott West to obtain the input from ASHRAE 189

- Ricson to obtain the input from ASHRAE 90.1

- If feasible, Scott is open to leading an RTAR effort

- Projects in-progress

| Team | Topic | Project Status- last meeting |
| --- | --- | --- |
| Landsberg (lead), Joe and Scott W. (reviewer) | RTAR-1822 “Alternate Expressions of Building EUI as Energy Performance Metrics” | Revised RTAR to be submitted soon |
| Boyd (lead) | MTG defensible measures of environmental and economic impact | WS was completed and went out for bids. Two or three bids (including Laurence Technical University) –No updates from this meeting |
| Nick Long | RTAR from “Building Data Exchange” | in progress |
| Landsberg, Carpenter, Joe Firrantello (lead) | RTAR 1872 -"Updating Site Energy Targets for ASHRAE Standard 100-2018 - Energy Efficiency in Existing Buildings" | There is a site/source discussion within TC. Terry has taken it independently from DOE. This project potentially can be removed from the list. |
| Kim – Liaison of TC2.1 | Thermal Comfort in U.S. and Canadian residences: Indoor conditions, occupant behavior and energy consumption | WS submitted to the subcommittee basecamp. Ready for review. Due by Feb. 16 |
| Boyd, TC9.9 | Data Center data set for RP-1771 | Needs RTAR (low priority)- |

- New Business/Topic

- Service to ASHRAE research award nomination due by Sept. 1, 2020.   Please let Eric Yang know the input.

- TC 7.6 has been asked to help develop, and co-sponsor an RTAR on the topic: “a software-based toolkit for the evaluation of the life cycle energy and greenhouse gas emissions for buildings, building components, and equipment.” The RTAR would be developed in cooperation with TC 2.8 (Building Environmental Impacts and Sustainability).  Currently, we have 9 of 15 votes.   The deadline is June 12, 2020.

- Jeff H. brought up a usable data set effort possibly from TC 7.6.  There are some various data processing tools; but it is not organized.   Jeff suggested a possible PTAR to provide industry broader available resources.  Nick and Eric are interested to participate.  Jeff will follow up on this topic.

- Adjourn

NEXT IN-PERSON MEETING:  June, 2020 –Austin, Tx