Meeting Minutes TC 7.6 Research Subcommittee Sunday Feb. 2, 2020, 1:00 PM–2:00 PM Lake George A Orlando, FL

- Sign-in / introductions

16 people attended (including two others without sign-in)

| Name | Affiliation | Email Address |
| --- | --- | --- |
| Eric Yang | Energy System Group | ericyangcem@gmail.com |
| Joe Firrantello (JF) | Envinity Inc. | j.firrantello@gmail.com |
| Michael Deru | NREL | Michael.deru@nrel.gov |
| Bruce Hunn | Consultant | hunnbuildingenergy@gmail.com |
| Jennifer Mott | California Polytechnic State University | jpeuker@calpoly.edu |
| Nicholas Long | NREL | nicholaslong@nrel.org |
| Curtis Fong | Taylor Engineering | cfong@taylor-engineering.com |
| Bill Murphy | RAC Liaison | William.murphy@uky.edu |
| Hyojin Kim | NJIT | Hyojin.kim@njit.edu |
| Joe Zhou | Slipstream | jzhou@slipstreaminc.org |
| Dennis Landsberg | L&S Energy | Dlandsberg@ls-energy.com |
| Lexuan Zhong | University of Alberta | lexuan.zhong@ualberta.ca |
| Ahmed Abdel-Salam | Rycom | Ahmed.abdel-salam@rycom.com |
| Yash Shukla | CARBSE | Yash.shukla@cept.ac.in |

- RP-1771 – Modeling of typical commercial buildings in support of the ASHRAE bEQ energy rating program

Principal investigator: Wangda Zuo; deadline is March 31, 2020.  One year no cost extension request to March 31, 2021.  18 prototype building types and eight climate zones.

- RP-1650 –TC 7.3, TC 7.6 co-sponsored – Training requirements for sustainable, high-performance building (HPB) operation

Montana State University is the principal contractor. The draft report is completed and approved by ASHRAE in May 2019.  The final report will be available from ASHRAE website soon.

- 1836-RTAR “Developing a Standardized Categorization System for Energy Efficiency Measures

The project goal/deliverables were rearranged; project advisory board met regularly.  Plan to complete by next summer.

- RP-1814 (co-sponsored with TC 2.8)– Actual Energy Performance of Secondary Schools and Medium Offices Designed to Comply with ASHRAE Standard 90.1-2010

Joe Z. shared that the scope was limited to only secondary schools with seven climate zones.  Team still collect the data; 12-month extension was requested.

- Recently completed projects

RP– 1633”Data and Interfaces for Advanced Building Maintenance and Operation” – completed; posted online.

RP–1651“Development of Maximum Technically Achievable Energy Targets for Ultra-Low Energy”– completed one year ago; good feedback from members

RP-1702 – Studies to test the performance measurement protocols (recently completed, goal achieved)

- Topics brought out last conference meeting

- How do the existing buildings (compliant with 90.1) meet the standard requirement of SSPC 100?

Interesting topic to explore further with input from ASHRAE 189 and 90.1

Action:

- Scott West to obtain the input from ASHRAE 189 and Joe F. to obtain the input from ASHRAE 100

- Carbon emission target (Scott Hackle, Michael Deru)

Not urgent.  Listed in the parking lot.

- ASHRAE TC1.4 meeting suggested a research project on the ‘costs and benefits of Cx building controls’, notably including the persistence and longevity impacts. (Scott Hackle)

Scott will mention it at TC 1.4 Research meeting again, and see if the others involved in the idea are making any progress or want to continue.

- Code compliance secondary research to inform 90.1.  (Scott Hackle)

Action:

- Scott West to obtain the input from ASHRAE 189

- Ricson to obtain the input from ASHRAE 90.1

- If feasible, Scott is open to leading an RTAR effort

- Projects in-progress

| Team | Topic | Project Status- last meeting |
| --- | --- | --- |
| Landsberg (lead), Joe and Scott W. (reviewer) | “Alternate Expressions of Building EUI as Energy Performance Metrics” | WS in progress; to be completed before the next conference. |
| Boyd (lead) | MTG defensible measures of environmental and economic impact | WS was completed and went out for bids. Two or three bids (including Laurence Technical University) –No updates from Boyd |
| Amanda, Scott | Further expansion of RP-1651 scope: on-site energy, cost, peak demand, emission, water, performance matrix | Amanda will take action to follow up with AEDG Committee (more collaboration); Jason Glazer to publish ASHRAE journals – it didn’t happen (updated) |
| Nick Long | RTAR from “Building Data Exchange” | in progress |
| Landsberg, Carpenter, Joe Firrantello (lead) | RTAR 1872 -"Updating Site Energy Targets for ASHRAE Standard 100-2018 - Energy Efficiency in Existing Buildings" | There is a site/source discussion within TC. Terry has taken it independently from DOE. This project potentially can be removed from the list. |
| Kim – Liaison of TC2.1 | Thermal Comfort in U.S. and Canadian residences: Indoor conditions, occupant behavior and energy consumption | WS submitted to the subcommittee basecamp. Ready for review. |
| Boyd, TC9.9 | Data Center data set for RP-1771 | Needs RTAR (low priority)- |
| Deru | Target finder based on RP-1771 | Needs RTAR (low priority)- |

- New Business/Topic

- Adjourn

NEXT IN-PERSON MEETING:  June, 2020 –Austin, Tx