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Meeting Minutes
TC 7.6 Research Subcommittee

Sunday Feb. 2, 2020, 1:00 PM–2:00 PM
Lake George A
Orlando, FL




1. [bookmark: _GoBack]Sign-in / introductions 
16 people attended (including two others without sign-in)

	Name
	Affiliation 
	Email Address

	Eric Yang 
	Energy System Group
	ericyangcem@gmail.com

	Joe Firrantello (JF)
	Envinity Inc.
	j.firrantello@gmail.com 

	Michael Deru
	NREL
	Michael.deru@nrel.gov

	Bruce Hunn
	Consultant
	hunnbuildingenergy@gmail.com 

	Jennifer Mott
	California Polytechnic State University
	jpeuker@calpoly.edu 

	Nicholas Long
	NREL
	nicholaslong@nrel.org 

	Curtis Fong
	Taylor Engineering
	cfong@taylor-engineering.com 

	Bill Murphy
	RAC Liaison 
	William.murphy@uky.edu

	Hyojin Kim
	NJIT
	Hyojin.kim@njit.edu

	Joe Zhou
	Slipstream
	jzhou@slipstreaminc.org 

	Dennis Landsberg
	L&S Energy
	Dlandsberg@ls-energy.com 

	Lexuan Zhong
	University of Alberta 
	lexuan.zhong@ualberta.ca

	Ahmed Abdel-Salam 
	Rycom 
	Ahmed.abdel-salam@rycom.com 

	Yash Shukla
	CARBSE
	Yash.shukla@cept.ac.in 




2. RP-1771 – Modeling of typical commercial buildings in support of the ASHRAE bEQ energy rating program
Principal investigator: Wangda Zuo; deadline is March 31, 2020.  One year no cost extension request to March 31, 2021.  18 prototype building types and eight climate zones.
3. RP-1650 –TC 7.3, TC 7.6 co-sponsored – Training requirements for sustainable, high-performance building (HPB) operation
Montana State University is the principal contractor. The draft report is completed and approved by ASHRAE in May 2019.  The final report will be available from ASHRAE website soon.
4. 1836-RTAR “Developing a Standardized Categorization System for Energy Efficiency Measures 
The project goal/deliverables were rearranged; project advisory board met regularly.  Plan to complete by next summer. 
5. RP-1814 (co-sponsored with TC 2.8)– Actual Energy Performance of Secondary Schools and Medium Offices Designed to Comply with ASHRAE Standard 90.1-2010
Joe Z. shared that the scope was limited to only secondary schools with seven climate zones.  Team still collect the data; 12-month extension was requested.
6. Recently completed projects

RP– 1633”Data and Interfaces for Advanced Building Maintenance and Operation” – completed; posted online.
RP–1651“Development of Maximum Technically Achievable Energy Targets for Ultra-Low Energy”– completed one year ago; good feedback from members
RP-1702 – Studies to test the performance measurement protocols (recently completed, goal achieved)

7. Topics brought out last conference meeting
	
a) How do the existing buildings (compliant with 90.1) meet the standard requirement of SSPC 100? 
Interesting topic to explore further with input from ASHRAE 189 and 90.1
Action: 
· Scott West to obtain the input from ASHRAE 189 and Joe F. to obtain the input from ASHRAE 100
b) Carbon emission target (Scott Hackle, Michael Deru)
Not urgent.  Listed in the parking lot. 
c) ASHRAE TC1.4 meeting suggested a research project on the ‘costs and benefits of Cx building controls’, notably including the persistence and longevity impacts. (Scott Hackle)
Scott will mention it at TC 1.4 Research meeting again, and see if the others involved in the idea are making any progress or want to continue.
d) Code compliance secondary research to inform 90.1.  (Scott Hackle)
Action: 
· Scott West to obtain the input from ASHRAE 189
· Ricson to obtain the input from ASHRAE 90.1
· If feasible, Scott is open to leading an RTAR effort

8. Projects in-progress

	Team
	Topic
	Project Status- last meeting

	Landsberg (lead), Joe and Scott W. (reviewer)
	“Alternate Expressions of Building EUI as Energy Performance Metrics”
	WS in progress; to be completed before the next conference. 

	Boyd (lead)
	MTG defensible measures of environmental and economic impact 
	WS was completed and went out for bids.  Two or three bids (including Laurence Technical University) –No updates from Boyd

	Amanda, Scott
	Further expansion of RP-1651 scope: on-site energy, cost, peak demand, emission, water, performance matrix  
	Amanda will take action to follow up with AEDG Committee (more collaboration); Jason Glazer to publish ASHRAE journals – it didn’t happen (updated)

	Nick Long
	RTAR from “Building Data Exchange” 

	 in progress

	Landsberg, Carpenter, Joe Firrantello (lead)
	RTAR 1872 -"Updating Site Energy Targets for ASHRAE Standard 100-2018 - Energy Efficiency in Existing Buildings"
	There is a site/source discussion within TC. Terry has taken it independently from DOE.  This project potentially can be removed from the list. 

	Kim – Liaison of TC2.1
	Thermal Comfort in U.S. and Canadian residences: Indoor conditions, occupant behavior and energy consumption
	WS submitted to the subcommittee basecamp.  Ready for review.    

	Boyd,  TC9.9 
	Data Center data set for RP-1771
	Needs RTAR (low priority)-

	Deru
	Target finder based on RP-1771
	Needs RTAR (low priority)-



9. New Business/Topic
10. Adjourn

NEXT IN-PERSON MEETING:  June, 2020 –Austin, Tx
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